## Start Here
LaunchReady — Implementation Portfolio Workbook
Independent simulated SaaS implementation ¦ Prepared by Hydi Maqousi ¦ All organizations, data, and outcomes are fictional.
HOW TO USE THIS WORKBOOK
Worksheet | Purpose | Competency demonstrated
Dashboard | Executive launch view, milestones, risks, defects, and simulated adoption metrics | Recruiter / hiring manager
Discovery | Client questions, simulated findings, and decisions | Business analysis
Requirements | Business, functional, data, reporting, security, and training requirements | Requirements gathering
Traceability | Requirement-to-design-to-test-to-status mapping | Implementation analysis
User Stories | User stories with acceptance criteria and priorities | Product / BA
Project Plan | Eight-week pilot implementation plan with dependencies | Project coordination
RACI | Ownership and participation model | Stakeholder management
RAID Log | Risks, assumptions, issues, and dependencies | Risk management
Decision Log | Key implementation decisions and rationale | Governance
Configuration | Workflow, roles, reminders, and business rules | Systems configuration
Data Readiness | Import template, mapping, intentional errors, and corrections | Data validation
UAT & Defects | UAT strategy, test cases, results, and defect tracker | Testing / QA
Enablement | Onboarding, training, quick-reference, knowledge-base, and handoff | Enablement
Go-Live | Readiness assessment, checklist, and hypercare plan | Launch readiness
Post-Launch | 30-day metrics, lessons learned, and Phase 2 backlog | Product operations
PORTFOLIO DISCLOSURE This workbook documents an independent simulated implementation. It does not represent a real customer engagement, production deployment, employer project, or verified business result. Simulated metrics are included to demonstrate analysis and measurement design.

## Dashboard
Executive Implementation Dashboard
Pilot launch: Northstar Community Services implementing LaunchReady Employee Operations Platform.
KPI | Baseline | Target | Simulated Day 30 | Status | LAUNCH SNAPSHOT
Avg. onboarding completion (days) | 9 | 6 | 5.8 | Met | Field | Value
Requests requiring follow-up | 32% | 15% | 12% | Met | Overall readiness | 100%
Missing first-day items | 21% | 8% | 7% | Met | UAT pass rate | 93.33%
Internal emails per hire | 14 | 6 | 5.4 | Met | Open launch blockers | 0
Requests submitted in platform | 0% | 90% | 93% | Met | Open high risks | 1
Required tasks completed |  | 95% | 96% | Met | Pilot locations | 2
Metric | Baseline | Day 30 | Target
Completion time | 9 | 5.8 | 6
Follow-up rate | 32 | 12 | 15
Missing items | 21 | 7 | 8
Emails per hire | 14 | 5.4 | 6
Platform adoption | 0 | 93 | 90
KEY IMPLEMENTATION TAKEAWAY
A controlled two-location pilot reduced risk while validating standardized intake, automated task assignment, centralized tracking, and measurable onboarding outcomes. Results shown are simulated for portfolio demonstration.

## Discovery
Discovery Questionnaire & Findings
Structured simulated interviews with HR Operations, IT, hiring managers, compliance, and the executive sponsor.
ID | Theme | Discovery question | Simulated finding / decision | Priority
D-01 | Business goals | What problem has the greatest impact? | No centralized status tracking; follow-up consumes HR capacity. | High
D-02 | Business goals | What defines success? | Faster completion, fewer errors, stronger compliance, and fewer emails. | High
D-03 | Process | Who initiates onboarding? | Hiring managers submit a standardized request. | High
D-04 | Process | Which steps vary? | Equipment, access, training, and documents vary by role/location. | High
D-05 | Process | Where do delays occur? | Incomplete intake and late IT notification. | High
D-06 | Users | Who needs access? | HR admins, managers, IT/facilities, compliance, executives, employees. | High
D-07 | Data | What data will be imported? | Active employees, pending hires, role/location mappings, manager relationships. | High
D-08 | Data | What data problems are expected? | Duplicates, invalid emails, missing managers, inconsistent locations/dates. | High
D-09 | Workflow | What should be automated? | Task creation, routing, reminders, escalation, completion notices. | High
D-10 | Security | What access rules apply? | Least privilege; managers see direct reports; executives see aggregate reporting. | High
D-11 | Testing | Who approves UAT? | HR Operations Director with IT and compliance sign-off. | High
D-12 | Launch | How should rollout occur? | Two-location pilot followed by six-location expansion. | High
D-13 | Support | How will issues be handled? | Central ticket queue, severity definitions, daily hypercare triage. | Medium
D-14 | Reporting | What metrics matter? | Cycle time, follow-up, overdue tasks, adoption, first-day readiness. | High

## Requirements
Business Requirements Document Register
Approved scope for the simulated pilot. Requirement IDs link to traceability and UAT.
Requirement ID | Type | Requirement | Priority | Owner | Status
BR-01 | Business | Provide one source of truth for onboarding status | Must | HR Ops | Approved
FR-01 | Functional | Managers can submit a standardized request with required fields | Must | Hiring Manager | Approved
FR-02 | Functional | System assigns tasks by employee role and location | Must | HR Ops | Approved
FR-03 | Functional | System sends reminders 3 days and 1 day before due date | Must | HR Ops | Approved
FR-04 | Functional | Overdue tasks escalate to the task owner’s manager after 1 day | Should | Executive Sponsor | Approved
FR-05 | Functional | Managers can view status for direct reports | Must | Hiring Manager | Approved
DR-01 | Data | Import employee, manager, role, location, email, and start date | Must | Data Lead | Approved
DR-02 | Data | Reject duplicates and invalid required-field values before import | Must | Data Lead | Approved
RR-01 | Reporting | Dashboard displays completion, overdue tasks, and cycle time | Must | Executive Sponsor | Approved
SR-01 | Security | Apply role-based access and least-privilege permissions | Must | IT Lead | Approved
SR-02 | Security | Maintain timestamped audit history for status and record changes | Must | Compliance | Approved
TR-01 | Training | Provide role-based admin and manager training before launch | Must | Training Lead | Approved
NR-01 | Nonfunctional | Core pages load within 3 seconds in pilot conditions | Should | IT Lead | Approved
NR-02 | Nonfunctional | Support current versions of Chrome and Edge | Should | IT Lead | Approved
BR-02 | Business | Reduce manual follow-up and email coordination | Must | HR Ops | Approved

## Traceability
Requirements Traceability Matrix
Maps each approved requirement to configuration, test evidence, and delivery status.
Requirement ID | Short name | Design / configuration | Test case(s) | Test result | Delivery status
BR-01 | Central status | Dashboard + shared record | TC-08 | Passed | Complete
FR-01 | Standard intake | Required-field form | TC-01, TC-02 | Passed | Complete
FR-02 | Automated tasks | Role/location workflow rules | TC-03 | Passed | Complete
FR-03 | Reminders | 3-day and 1-day notifications | TC-04 | Passed | Complete
FR-04 | Escalation | 1-day overdue escalation | TC-05 | Passed after retest | Complete
FR-05 | Manager visibility | Manager security view | TC-06 | Passed | Complete
DR-01 | Data import | CSV import mapping | TC-09 | Passed | Complete
DR-02 | Data quality | Validation rules and exception file | TC-10 | Passed | Complete
RR-01 | Dashboard | Operational metrics dashboard | TC-08 | Passed | Complete
SR-01 | RBAC | Permission profiles | TC-06, TC-07 | Passed | Complete
SR-02 | Audit trail | Timestamped history | TC-11 | Passed | Complete
TR-01 | Training | Admin + manager sessions | TC-12 | Passed | Complete
NR-01 | Performance | Pilot performance check | TC-13 | Passed | Complete
NR-02 | Browsers | Browser compatibility | TC-14 | Passed | Complete
BR-02 | Reduce manual work | Automation + dashboards | TC-04, TC-08 | Passed | Complete

## User Stories
User Stories & Acceptance Criteria
Stories translate business needs into testable platform behavior.
Story ID | User story | Acceptance criteria | Priority | Requirement link
US-01 | As a hiring manager, I want a guided request form so that HR receives complete information. | Given a new request, when required fields are missing, then submission is blocked and fields are identified. | Must | FR-01
US-02 | As HR, I want tasks generated automatically so each department knows its responsibilities. | Given a valid request, when submitted, then the correct role/location checklist is created within one minute. | Must | FR-02
US-03 | As a task owner, I want reminders so that deadlines are not missed. | Given an incomplete task, when it is 3 or 1 day from due, then the owner receives one reminder. | Must | FR-03
US-04 | As a manager, I want to see direct-report status so I can remove blockers. | Given an assigned direct report, when the manager opens the dashboard, then only authorized records are visible. | Must | FR-05/SR-01
US-05 | As compliance staff, I want an audit history so I can verify completion evidence. | Given a record change, when saved, then user, timestamp, previous value, and new value are retained. | Must | SR-02
US-06 | As an executive, I want aggregate metrics so I can evaluate adoption and cycle time. | Given completed records, when filters are applied, then totals and rates match source records. | Must | RR-01
US-07 | As a data lead, I want invalid records rejected so that bad data does not enter the platform. | Given a file with errors, when validated, then invalid rows are rejected with field-level reasons. | Must | DR-02

## Project Plan
Eight-Week Pilot Implementation Plan
Two-location pilot followed by a controlled go/no-go decision and expansion recommendation.
Phase | Work item | Owner | Start | Finish | Status | Dependency
1. Discovery | Kickoff and stakeholder interviews | Implementation Lead | 2026-09-07 | 2026-09-11 | Complete | None
1. Discovery | Current-state process validation | Business Analyst | 2026-09-09 | 2026-09-14 | Complete | Interviews
2. Requirements | BRD, stories, and sign-off | Implementation Lead | 2026-09-14 | 2026-09-18 | Complete | Discovery
3. Design | Future-state and configuration design | Solution Consultant | 2026-09-21 | 2026-09-25 | Complete | Requirements
4. Data | Extract, clean, map, and validate pilot data | Data Lead | 2026-09-21 | 2026-10-02 | Complete | Requirements
5. Configure | Configure roles, workflows, notifications, dashboards | Solution Consultant | 2026-09-28 | 2026-10-09 | Complete | Design
6. Test | System test and defect correction | Vendor QA | 2026-10-05 | 2026-10-13 | Complete | Configuration
6. Test | Customer UAT and sign-off | UAT Lead | 2026-10-12 | 2026-10-16 | Complete | Data + system test
7. Enable | Admin and manager training | Training Lead | 2026-10-14 | 2026-10-20 | Complete | UAT stable
8. Launch | Readiness review and go/no-go | Executive Sponsor | 2026-10-20 | 2026-10-21 | Complete | UAT + training
8. Launch | Pilot go-live | Implementation Lead | 2026-10-22 | 2026-10-22 | Complete | Go decision
9. Hypercare | Daily triage and adoption monitoring | Support Lead | 2026-10-22 | 2026-11-05 | Complete | Go-live
10. Review | 30-day review and Phase 2 recommendation | Implementation Lead | 2026-11-20 | 2026-11-20 | Complete | Metrics

## RACI
RACI & Stakeholder Matrix
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Deliverable / decision | Implementation Lead | Executive Sponsor | IT Lead | Data Lead | HR/UAT Lead | Managers
Discovery & requirements | R | A | C | C | C | I
Configuration design | A | C | R | C | C | I
Data preparation | A | C | C | R | C | I
Security review | C | I | R | C | A | I
UAT execution | A | C | C | C | R | I
Training | A | C | C | I | R | I
Go/no-go decision | R | A | C | C | C | I
Hypercare | A | I | R | C | C | I
Post-launch review | R | A | C | C | C | I

## RAID Log
RAID Log
Active management of risks, assumptions, issues, and dependencies across the pilot.
ID | Type | Description | Impact | Likelihood / State | Owner | Response / mitigation | Status
R-01 | Risk | Incomplete source data delays import | High | Medium | Data Lead | Run validation twice; require owner sign-off | Open
R-02 | Risk | Managers do not adopt new intake process | High | Medium | Training Lead | Role-based training; office hours; adoption dashboard | Monitoring
R-03 | Risk | Notifications create duplicate messages | Medium | Low | Solution Consultant | Test all trigger combinations | Closed
A-01 | Assumption | Pilot locations provide UAT participants | Medium | Low | Executive Sponsor | Confirm roster by end of Week 4 | Validated
A-02 | Assumption | Current browsers meet requirements | Low | Low | IT Lead | Compatibility test | Validated
I-01 | Issue | Overdue escalation initially routed to HR instead of manager | High | Resolved | Solution Consultant | Corrected rule and retested in TC-05 | Closed
I-02 | Issue | Four duplicate employee IDs found in extract | Medium | Resolved | Data Lead | Merged records and documented survivorship rule | Closed
D-01 | Dependency | Security role approval required before UAT | High | Medium | IT Lead | Approval checkpoint in Week 5 | Complete
D-02 | Dependency | Training roster depends on pilot manager list | Medium | Low | HR/UAT Lead | Reconcile list before invitations | Complete

## Decision Log
Implementation Decision Log
Recorded decisions preserve rationale and reduce rework.
Decision ID | Date | Decision | Rationale | Status | Approver
DEC-01 | 2026-09-10 | Use centralized tracking as primary project objective | HR spends significant time requesting status | Approved | Executive Sponsor
DEC-02 | 2026-09-12 | Hiring managers submit onboarding requests | Places data entry closest to the source | Approved | HR Director
DEC-03 | 2026-09-18 | Pilot two locations before organization-wide rollout | Limits change risk and creates learning cycle | Approved | Executive Sponsor
DEC-04 | 2026-09-24 | Reject invalid import rows instead of partially loading | Protects data integrity and creates auditable correction queue | Approved | Data + IT Leads
DEC-05 | 2026-10-02 | Escalate one day after task due date | Balances accountability with notification volume | Approved | HR Director
DEC-06 | 2026-10-16 | Proceed with pilot after medium defects are mitigated | No open critical/high defects; workarounds documented | Approved | Go/No-Go Team

## Configuration
Configuration Requirements
Functional configuration translated from approved requirements and user stories.
Config ID | Component | Rule / setting | Scope | Requirement | Status
CFG-01 | Intake form | Employee ID, name, email, start date, manager, role, location required | All pilot locations | FR-01 | Configured
CFG-02 | Workflow | Generate checklist from role + location mapping | All requests | FR-02 | Configured
CFG-03 | Notification | Reminder at 3 days and 1 day before due date | Incomplete tasks only | FR-03 | Configured
CFG-04 | Escalation | Notify task owner manager 1 day overdue | Exclude completed/cancelled | FR-04 | Configured
CFG-05 | Permissions | Managers view direct reports; contributors edit assigned tasks | Least privilege | SR-01 | Configured
CFG-06 | Audit | Record user, timestamp, old value, new value | Tracked fields | SR-02 | Configured
CFG-07 | Dashboard | Show cycle time, overdue tasks, adoption, completion | Executive aggregate + manager scope | RR-01 | Configured
CFG-08 | Email | Send completion confirmation to manager and HR | Once per onboarding record | BR-02 | Configured

## Data Readiness
Data Import, Mapping & Validation
Sample records intentionally include errors; corrected values demonstrate the validation workflow.
Employee ID | First Name | Last Name | Email | Start Date | Location Code | Manager ID | Role | Validation Error | Correction | Final Status
E1001 | Amina | Rahman | amina.rahman@northstar.org | 2026-10-26 | LOC-BUF | M202 | Care Coordinator | Valid |  | Ready
E1002 | Daniel | Kim | daniel.kimnorthstar.org | 2026-10-27 | LOC-BUF | M202 | Analyst | Invalid email | daniel.kim@northstar.org | Corrected
E1003 | Sofia | Lopez | sofia.lopez@northstar.org |  | LOC-ROC | M310 | Program Assistant | Missing start date | 2026-10-28 | Corrected
E1004 | Omar | Haddad | omar.haddad@northstar.org | 2026-10-29 | Buffalo | M202 | IT Support | Invalid location code | LOC-BUF | Corrected
E1004 | Omar | Haddad | omar.h@northstar.org | 2026-10-29 | LOC-BUF | M202 | IT Support | Duplicate employee ID | Remove duplicate row | Corrected
E1006 | Mei | Chen | mei.chen@northstar.org | 2026-11-02 | LOC-ROC |  | Case Manager | Missing manager ID | M310 | Corrected
E1007 | Noah | Williams | noah.williams@northstar.org | 11/03/26 | LOC-BUF | M202 | Facilities Associate | Nonstandard date | 2026-11-03 | Corrected
E1008 | Layla | Saleh | layla.saleh@northstar.org | 2026-11-04 | LOC-ROC | M310 | Compliance Specialist | Valid |  | Ready
Source field | Target field | Data type | Required | Transformation / rule | Owner
employee_id | Employee ID | Text | Yes | Unique; trim spaces | HRIS
work_email | Email | Text | Yes | Lowercase; valid email pattern | HRIS
hire_date | Start Date | Date | Yes | Convert to YYYY-MM-DD | HRIS
site | Location Code | Text | Yes | Map approved aliases to location code | HR Ops
supervisor_id | Manager ID | Text | Yes | Must exist in manager reference | HRIS
job_title | Role | Text | Yes | Map to approved role catalog | HR Ops

## UAT & Defects
UAT Strategy, Test Results & Defect Tracker
Exit criteria: 100% critical scenarios executed; no open critical/high defects; at least 90% overall pass rate.
Test ID | Scenario | Role | Expected result | Result | Requirement | Defect
TC-01 | Submit valid onboarding request | Manager | Request created; required fields saved | Pass | FR-01
TC-02 | Attempt submission with missing manager | Manager | Submission blocked; manager field identified | Pass | FR-01
TC-03 | Generate tasks for role/location | HR Admin | Correct checklist and owners created | Pass | FR-02
TC-04 | Send scheduled reminders | Task Owner | One reminder at each configured interval | Pass | FR-03
TC-05 | Escalate overdue task | HR Admin | Manager receives escalation after 1 day | Pass after retest | FR-04 | DEF-01
TC-06 | Manager views direct reports | Manager | Only assigned direct reports visible | Pass | FR-05/SR-01
TC-07 | Attempt unauthorized employee access | Manager | Access denied and event logged | Pass | SR-01
TC-08 | Reconcile dashboard metrics | Executive | Metrics match source records | Pass | RR-01
TC-09 | Import valid CSV | Data Lead | All valid records loaded once | Pass | DR-01
TC-10 | Import invalid CSV | Data Lead | Invalid rows rejected with reasons | Pass | DR-02
TC-11 | Review audit history | Compliance | All tracked changes retain history | Pass | SR-02
TC-12 | Complete training scenario | Manager | User completes request without assistance | Pass | TR-01
TC-13 | Pilot page response | IT | Core pages load within 3 seconds | Pass | NR-01
TC-14 | Chrome and Edge checks | IT | Core functions work in both browsers | Pass | NR-02
TC-15 | Cancel onboarding request | HR Admin | Open tasks cancelled; history retained | Fail / workaround | FR-02 | DEF-02
Defect ID | Description | Severity | Status | Resolution / mitigation | Evidence
DEF-01 | Escalation routed to HR instead of manager | High | Closed | CFG-04 corrected | Retested TC-05
DEF-02 | Cancelled request leaves one facilities task open | Medium | Mitigated | Documented admin workaround; Phase 2 fix | Accepted for pilot
DEF-03 | Dashboard export filename lacks date | Low | Open | Backlog | Does not block launch

## Enablement
Onboarding, Training & Admin Handoff
Role-based enablement supports adoption while minimizing meeting-heavy support.
Audience | Format | Topics | Status | Owner
HR Administrators | 90-minute live session + recording | Configuration, exceptions, reporting, audit history | Complete | Training Lead
Hiring Managers | 45-minute live session + quick guide | Submit requests, monitor status, correct returns | Complete | Training Lead
Task Owners | 30-minute demonstration | Complete tasks, attach evidence, respond to reminders | Complete | Department Leads
Executives | 20-minute briefing | Dashboard interpretation and escalation path | Complete | Implementation Lead
New Employees | Automated welcome guide | Complete assigned forms and view status | Ready | HR Ops
QUICK-REFERENCE: SUBMIT A NEW-HIRE REQUEST
1 | Open New Hire > Create Request | Use the platform navigation; do not email HR.
2 | Complete required fields | Employee, role, manager, location, start date, and work email.
3 | Review generated checklist | Confirm department tasks match the employee role and location.
4 | Submit and monitor | Use the status dashboard; respond to returned fields.
5 | Escalate exceptions | Use the support link for access issues or incorrect workflows.
KNOWLEDGE-BASE ARTICLE: CORRECT A RETURNED REQUEST
If a request is returned, open the notification link, review the field-level message, update only the identified fields, and select Resubmit. The original submission and correction remain in the audit history. If the requested change affects the employee ID, location, or manager relationship, contact the HR administrator before resubmitting.

## Go-Live
Go-Live Readiness & Hypercare
Readiness score is a transparent evidence-based assessment, not a production claim.
Readiness area | Status | Weight | Score | Evidence
Requirements approved | Complete | 10 | 10 | Signed requirements register
Configuration complete | Complete | 15 | 15 | Configuration review
Data validation complete | Complete | 15 | 15 | Exception report cleared
UAT exit criteria met | Complete | 20 | 20 | 14/15 passed; medium defect mitigated
Security approval | Complete | 10 | 10 | Role matrix approved
Training complete | Complete | 10 | 10 | Attendance + recording
Support model active | Complete | 10 | 10 | Queue and escalation tested
Communications sent | Complete | 5 | 5 | Launch notice delivered
Rollback decision documented | Complete | 5 | 5 | Go/no-go minutes
TOTAL |  |  | 100
Hypercare cadence | Time / trigger | Participants | Output | Owner
Daily triage | 10:00 AM for 10 business days | Implementation, HR, IT, support | Prioritized issue list | Implementation Lead
Critical escalation | Within 30 minutes | Sponsor, IT, vendor | Incident decision | Support Lead
Adoption review | Every 2 business days | HR + implementation | Usage actions | HR Ops
Closeout | End of Day 10 | Core team | Hypercare summary | Implementation Lead

## Post-Launch
30-Day Post-Launch Review
Simulated pilot results demonstrate measurement design, analysis, and improvement recommendations.
Metric | Baseline | Target | Simulated Day 30 | Outcome | Recommended action
Average completion time (days) | 9 | 6 | 5.8 | Met | Continue weekly monitoring
Requests requiring follow-up | 32% | 15% | 12% | Met | Add inline field examples
Missing first-day items | 21% | 8% | 7% | Met | Keep daily exception view
Internal emails per hire | 1400% | 600% | 540% | Met | Move questions into ticket queue
Platform adoption | 0% | 90% | 93% | Met | Target non-adopters
Required tasks completed |  | 0.95 | 0.96 | Met | Review overdue patterns by department
Lesson learned | Evidence | Phase 2 recommendation
Data cleanup must begin before configuration ends | Duplicates and manager gaps required owner decisions | Add pre-import profiling report
Pilot managers needed scenario-based training | Practice reduced support questions | Convert training into self-paced modules
Severity definitions accelerated decisions | Medium defect was accepted with a documented workaround | Embed severity and acceptance workflow
Dashboard ownership must be explicit | HR and executives used different filters | Create standardized dashboard views
Role/location mapping needs governance | New roles can create checklist gaps | Add monthly configuration review
Phase 2 item | Value | Effort | Priority | Owner | Timing
Expand to remaining six locations | High | Medium | 1 | Implementation Lead | Next 60 days
Self-paced training modules | Medium | Medium | 2 | Training Lead | Next 60 days
HRIS API integration | High | High | 3 | IT Lead | Future release
Mobile task completion | Medium | High | 4 | Product Owner | Future release
Predictive delay alerts | Medium | High | 5 | Analytics Lead | Future release